## Sheet3
Task Name | Description | Objective | Start | Finish | Actual Start | Actual Finish | Resources | Last Update
201 Nucleoside Phosphonate Prodrugs |  |  | Mon 1/2/12 | Fri 7/20/18 | Mon 1/2/12
Publications
rewrite of CDV-Tyr-Amides Intracell Metab and potency - Simon | outline rewrite |  | 2018-05-15 | 2018-05-25 | 2018-05-15
rewrite of CDV-Tyr-Amides Intracell Metab and potency - Simon | first draft |  | 2018-05-25 | 2018-06-01
rewrite of CDV-Tyr-Amides Intracell Metab and potency - Simon | updated figures/tables |  | 2018-05-21 | 2018-06-01
rewrite of CDV-Tyr-Amides Intracell Metab and potency - Simon | second draft |  | 2018-06-08 | 2018-06-15
rewrite of CDV-Tyr-Amides Intracell Metab and potency - Simon | revised figures/tables |  | 2018-06-08 | 2018-06-15
rewrite of CDV-Tyr-Amides Intracell Metab and potency - Simon | submit to new journal |  | 2018-06-25 | 2018-06-29